## Sheet1
ID |  | Owner | Risk Summary | Risk Details | Progress | Area | Mitigation Strategy | Likelihood | Impact | Exposure
1 | ATC |  | Camera | delays in construction or delivery |  | Camera | work on V2 packages | 3 | 2 | 6
2 | ATC |  | Detector | unforseen detector peculiarities |  | Camera | liaise with WFCAM team | 2 | 3 | 6
3 | JAC |  | Commissioning | delays in installation/commissioning | camera delivery delayed. Work begun on V2 packages | Telescope | work on V2 packages | 2 | 2 | 4
4 | Casu |  | New Hire | recruitment delays | Hired JMI | Personnel | temporary hire | 3 | 1 | 3
5 | Casu |  | Key staff | loss to other lucrative jobs |  | Personnel | replace + good documentation | 1 | 3 | 3
6 | Casu |  | Serious Illness | loss of staff to prolonged illness (months-year) |  | Personnel | temporary hire, 4 week contingency | 2 | 4 | 8
7 | Casu |  | Minor Illness | short term loss of staff to less serious illness (<weeks) |  | Personnel | 4 week contingency | 4 | 2 | 8
6 | Casu |  | Software | problems in development of new algorithms |  | Software | be smarter | 2 | 2 | 4
7 | Casu |  | Reprocessing | bug fixes and improvements to algorithms |  | Software | allowed for | 4 | 3 | 12
8 | Casu |  | Hardware | setup and delivery delays |  | Hardware | commodity products | 1 | 4 | 4
9 | Casu |  | Disk failure | loss of raw data due to disk crash/failure |  | Hardware | raid systems and offline backup | 2 | 2 | 4
10 | Casu |  | Building Refurbishment | APM building refurbished during VDFS WFCAM processing. Disruption of staff offices and computing systems |  | Building/ Hardware | move hardware. Try to accelerate building work to happen prior to WFCAM commissioning | 4 | 3 | 12
11 | JAC/Casu/WFAU |  | Data volume | data transfer problems |  | Media/ Network | scheduled gaps for WFCAM on telescope | 3 | 4 | 12

## Sheet2
|  | Designation | Definitions
Likelihood | 1 | rare | Occur in exceptional circumstances
| 2 | possible | Might occur
| 3 | likely | Quite likely to occur
| 4 | almost certain | Will almost certainly occur
Impact | 1 | Insignificant | minor delay (<1 month), insignifcant cost
| 2 | Minor | delay 1-3 months, moderate cost, some loss of reputation
| 3 | Moderate | delay 3-12 months, signifcant cost, moderate loss of reputation
| 4 | Major | delay > 1 yr, large overspend